## Sheet1
Sr. No | Section | Task Details | Notes | Estimated Time Man Days
SITE ADMIN SECTION
1.1 | Admin Users Management | 1> Admin Login, 2> Admin Dashboard, 3> Modify Own Profile 4> Manage admin users (franchise site admin, dataentry operators) 5> Modify admin users. 6> Create admin users. 7> Change Status | There are three types of admin level users. 1> Admin - site admin or super admin. 2> Franchise admin - the admin of franchise domain site. 3> Data entry operator | 4
1.2 | Access Control for admin users | 1> Assign/Modify Access of admin modules by admin user type. |  | 1
1.3 | User Management | 1> Frontend registered users listing 2> Add, 3> Modify ,4> Change Status |  | 2
1.4 | Category Management | 1> Category Listing 2> Add, 3> Modify, 4> Delete |  | 0.5
1.5 | Sub Category Management | 1> Sub Category Listing 2> Add, 3> Modify, 4> Delete |  | 0.5
1.6 | Country | 1> Country Listing 2> Add, 3> Modify, 4> Delete |  | 0.5
1.7 | State/Province | 1> state Listing 2> Add, 3> Modify, 4> Delete |  | 0.5
1.8 | City | 1> City Listing 2> Add, 3> Modify, 4> Delete | * RnD required for fetching Latitude and Longitude using API. | 0.5
1.9 | Zip | 1> Zip Listing 2> Add, 3> Modify, 4> Delete | * RnD required for fetching Latitude and Longitude using API. | 0.5
1.10 | Popular Location | 1> Location Listing 2> Add, 3> Modify, 4> Delete | * RnD required for fetching Latitude and Longitude using API. * Where does we will get the records of locations? | 0.5
1.11 | Zip Location Mapping | 1> Mapping zip and location listing. | * Where does we will get the records of locations? | 0.25
1.12 | Autosuggestion | 1> Listing By Approved/User suggested 2> Add, 3> Modify, 4> Delete |  | 0.75
1.13 | Document Verification Management | 1> Listing of Documents required 2> Add, 3> Modify, 4> Delete 5> Listing Of User Document Verified 6> Add, 7> Modify, 8> Delete |  | 2
1.14 | CMS | 1> Listing cms contents 2> Modify |  | 0.25
1.15 | Themes | 1> Listing Themes 2> Add, 3> Modify, 4> Delete 5> Listing Franchise Selected Theme 6> Change Status |  | 1
1.16 | Users Public Private Fields | 1> Assign which Fields of Users are Public, Private Or Members only. |  | 0.5
1.17 | Service Extended Defination | 1> Listing Service Extended fields. 2> Modify | * Critical senerio is putting the field values for different category -> sub category. | 2
1.18 | Report Abuse | 1> Listing 2> change status |  | 0.25
1.19 | Franchisee Domain | 1> Listing of franchisee users and their domains 2> Add, 3> Modify, 4> Delete |  | 0.75
Frontend User Section
2.1 | User Registration | 1> Registration 2> Signup Using Facebook Login 3> Signup Using Linkedin, As per discussion 4Oct, this is not in this scope of project. 4> Email Verification 5> Login 6> Forget Password 7> After user registers or login user will goto dashboard. Follow section 2.5 | * What is business name in registration form? >>on meeting 4oct, it will be changed to display name. | 2.5
2.2 | Edit Profile | 1> Basic Info 2> Educational Info (Add more) 3> Profesional Info (Add more) 4> Change Image 5> List profile 6> Guru profile | * What do you mean by "This will come as popup" ? * What will happen if user clicks "Tweet my profile" , "Post my profile to facebook"? * Where user will goto by clicking "list profile" and "guru profile"? | 2
2.2.1 | Service / Category Name | 1> This link will take user to "Country Of Service" page. Please follow point 2.3.1 below.
2.2.2 | Tweet My Profile |  | * What to do?
2.2.3 | Post my profile to facebook | 1> As discussed on 4Oct, It will post a link to wall. | * Which profile fields to be posted and where(wall) ? | 0.5
2.2.4 | Be a Guru Verified | 1> Verified 2> Facebook connect 3> Unverified 4> Phone number verify. Add a phone number. 5> Make Me feature. What is the process? 6> Add more services. What will happen when a user clicks here? | * The left side menu has changed. * What do you mean by verified and unverified on "http://91.biz/o/guru/guru_listed_21sep/guru/Profile/trust_1.jpg" * After add a phone number Where does the user will put the verification code?
2.2.5 | Verify your mobile | No wire frame found. | What to do?
2.3 | User Services
2.3.1 | Country Of Service | 1> Select the service country by loggedin user. User can select either USA or India. 2> Once inserted this field will be not editable. What will be the process if user wants to change the country? |  | 0.25
2.3.2 | Select Service Name | 1> User can add/modify his service name. | * In the wireframe there is "search service name" field. What is the purpose of this field? * Below in the service profile we found description. But here description field is missing | 0.25
2.3.3 | Select a Category | 1> Select a category 2> Select a sub category 3> Select a Specilization 4> User can add/modify category, sub category. 5> Add, Edit, Delete Specilization | * In the wireframe there is "upto 3 subcategories". But our system only allows one subcategory. Because there are more than one extended fields associated with subcategory. | 0.5
2.3.4 | Select Location | 1> Select city 2> Select zip 3> Select multiple(max-3) localities. 4> Suggest a locality 5> Add, Edit, Delete | * How locality suggestion will be managed? | 1.5
2.3.5 | Online Services | 1> Choose skype id 2> Choose yahoo id 3> choose gtalk id 4> Add, Edit |  | 0.25
2.3.6 | Tutoring Location |  | * This page refering to the same "Select location" page in wire frame. What is the purpose of this page?
2.3.7 | Classes | 1> Select Classes 2> Suggest a Class 3> Add, Edit | * I think this menu is for category tutor. | 0.25
2.3.7 | Subjects | 1> Select Subjects 2> Suggest a Subjects 3> Add, Edit | * I think this menu is for category tutor. Can user add multiple Subjects? * If a user Selects category "Dentis" then does this menu will appear? In that can what will happen? | 1
2.3.8 | Language | 1> Select Languages 2> Suggest a Languages 3> Add more 4> Add, Edit, Delete | * The left side menu has changed. * what is the purpose of "Select Mdium"? | 0.5
2.3.9 | Terms and Condition | 1> Accept terms. | * What will happen if user does not checks this field? | 0.25
2.4 | Send Message To Members | 1> Send email Message . | * Where does the link will appear? * How to select the email address to whome message to be send? | 0.25
2.5 | Dashboard | 1> Top Menu : - Dashboard(Selected), Profile, Service profile, Inbox, Notification, Testimony 2> Picture, Edit profile link (see section 2.2) 3> Verification:- Mobile verified, Email verified, "+ Add more" 4> Your services. "Add more services" 5> Alerts. 6> Inbox. We don't have internal messaging system. Do we want to implement it? Or Not in the scope of this project. 7> Notifications | * What will happen if user click "add more" link at Verification block? * What will happen if user click "add more" link at Your service block? * What type of data will appear in alerts? Also there is a close button, what will happen when user click that? * What type of data will appear in Notifications? | 1
2.6 | Profile | 1> Basic Info 2> Know About Service 3> Educational Info 4> Profesional Info 5> Certification 6> Contact Info 7> Profile Picture 8> Connect Me Button, As per discussion 4Oct, this is not in this scope of project. 9> Connected People, This will display all friends connected in facebook account of the user. 10> Share with friend, As per discussion 4Oct, this is not in this scope of project. 11> share via facebook, As discussed on 4Oct, It will post a link to wall. Please follow section 2.2.3 12> Share via twitter. Please follow section 2.2.2 13> In the right side panel block "50 people connected". As per discussion 4Oct, this is not in this scope of project. 14> Right side block "You are not connected". | * What will happen when user click "Know About Service"? * What do you mean by certification? | 1.5
2.6.1 | Know About Service | No wire frame found.
2.6.2 | Add your friend | No wire frame found.
2.7 | Service Profile | 1> Service related banner, As per discussion 4Oct, this will be ads posted by admin. 2> Like it 3> Recomend it 4> Bookmark 5> Service Description 6> Qualification 7> Subjects 8> Classes 9> Profile Picture 10> Contact Me 11> about 12> View full profile 13> Connected People, see section 2.6 14> Share with Friend, see section 2.6 15> Share via facebook, see section 2.6 16> Share via twitter, see section 2.6 17> In the right side panel block "50 people connected". see section 2.6 18> Right side block "You are not connected". see section 2.6 19> Take the service 20> Testimonial, Write Testimonial | * What will happen when user click "Like it"? * What will happen when user click "Recomend it"? * What will happen when user click "Bookmark"? * Where does user will add service description? * What will happen when user clicks "Contact me"? * What will happen when user clicks "View full profile"? | 2
2.7.1 | Like it | No wire frame found.
2.7.2 | Recomend it | No wire frame found.
2.7.3 | Bookmark | No wire frame found.
2.7.4 | Contact Me | No wire frame found.
2.7.5 | View full profile | No wire frame found.
2.7.6 | Take the service | * This section will be completed in section 2.7 |  | 0
2.7.7 | Write Testimonial | 1> Submit the feedback form. No wire frame found.
2.8 | Inbox | No wire frame found.
2.9 | Notification | As per discussion 4Oct, this is not in this scope of project.
2.10 | Testimony | No wire frame found.
Frontend Franchisee User Section
3.1 | Franchisee Registration | 1> Registration 2> Signup Using Facebook Login 3> Signup Using Linkedin 4> Email Verification 5> Login 6> Forget Password 7> After user registers or login user will goto dashboard. Follow section 2.5 * This section will be completed in section 2.1 | * After user logins, where should the user lands? * What is business name in registration form? | 0
3.2 | Edit Profile | 1> Basic Info 2> Educational Info (Add more) 3> Profesional Info (Add more) 4> Change Image 5> List profile 6> Guru profile * This section will be completed in section 2.2 | * What do you mean by "This will come as popup" ? * What will happen if user clicks "Tweet my profile" , "Post my profile to facebook"? * Where user will goto by clicking "list profile" and "guru profile"? | 0
3.2.1 | Service / Category Name |  | * Where should this link goto?
3.2.2 | Tweet My Profile | * This section will be completed in section 2.2.2 | * What to do? | 0
3.2.3 | Post my profile to facebook | * This section will be completed in section 2.2.3 | * Which profile fields to be posted and where(wall) ? | 0
3.2.4 | Be a Guru Verified | 1> Verified 2> Facebook connect 3> Unverified 4> Phone number verify. Add a phone number. 5> Make Me feature. What is the process? 6> Add more services. What will happen when a user clicks here? * This section will be completed in section 2.2.4 | * The left side menu has changed. * What do you mean by verified and unverified on "http://91.biz/o/guru/guru_listed_21sep/guru/Profile/trust_1.jpg" * After add a phone number Where does the user will put the verification code? | 0
3.2.5 | Verify your mobile | No wire frame found. * This section will be completed in section 2.2.5 | What to do? | 0
3.3 | Franchisee Services | Will franchisee users can update the below section using their domain admin also?
3.3.1 | Select Location | 1> Country Dropdown 2> Location [All, India, States], What is the functionality of this? 3> Zip 4> City 5> Add more location 6> Suggest a location | * Is there any limit for add more location? Sya 3 or 5 locations can be added. * No field for selecting State. | 1
3.3.2 | Select Language | 1> Select Languages 2> Suggest a Languages 3> Add more 4> Add, Edit, Delete |  | 0.5
3.3.3 | Select Sub Domain Prefix | 1> Select Sub Domain Prefix 2> Add 3> Check avability | * I think, user must be restricted to modify this field. | 0.5
3.3.4 | Select Domain | 1> Select Domain, add, non editable 3> Facebook api, editable 4> Linked in api, editable *Not in this scope of project 5> Google ads sense, editable | * What value will be taken in Google ads sense field? | 0.5
3.3.5 | Select Category | No wire frame found. | What to do?
3.3.6 | Select Theme | 1> Select Theme, Predifined theme by Admin 2> Add, Edit |  | 0.25
3.3.7 | SEO | 1> Meta tag 2> Meta Description 3> Meta Keywords 4> Add, Edit | * Will this meta information be set for all pages in franchisee domain? | 0.25
3.4 | Dashboard | No wire frame found. * This section will be completed in section 2.5 |  | 0
Frontend Section(Visitor, User, Franchisee)
4.1 | Home | 1> Top Nav Menu -> Profile , Guru(Selected), Rate, Property 2> Signup/Signin 3> Country Dropdown 4> Search Box :- Items=> Service, People Keywords, City/zip, Distance (kms radius) 5> Browse Members By Alphabates. 6> Popular Categories. 7> Recent Activity. 8> Ads posted by admin 9> Upon submit it will goto search result page. | * Please explain the "Profile , Rate, Property". Will these be redirecting to other external links. * Does we list all members who's name starts with letter "A" or "B" or "Z"? * What is criteria of finding popular category? Is there any limit of displaying these categories? Say only 10 popular categories to be shown. * What will be shown in the recent activity? | 1
4.2 | Search Result Page | 1> List the users who matches the search criteria. 2> Search box :- Service, Location, Distance. 3> Keep filter search. That will store the search criteria temporarily. 4> Users:- Featured, Certified, Verified. 5> Search Labels:- You searched for "keyword", "City", "Save Search", Within "radius" Kms, "Change". Search result city "Change" ("Show online result across city") 6> Records per page drop down 7> Sort results drop down. We may add this feature. 8> Refine Search, Clear search . 9> Text box and "Refine Search" button. 10> Right Side Sections Of Extended Services, Which users and filter by more options. This Small boxes (Blocks) are completely dependent upon category selected by the user. If no category is selected(searched by people name) then we will list all categories. 11> Under each blocks in right side panel, there are "Refine" button and "+ Add more in list". 12> At bottom of the right side panel there is a block "All members in circle". | * RND required for searching algorithm. * Within the search box where to show, if a user search for people from home page? * What do you mean by Certified? * What will happen when user clicks "Refine Search" link? * What will happen when user clicks "Refine Search" button? * Under each blocks in right side panel, there are "Refine" button and "+ Add more in list". What are the functionality of these? | 15
4.2.1 | Profile listing | 1> Service Name, 2> Connect Label 3> 3rd *, What is the meaning of the "*" symbol, after the connection label? 4> Service provider name 5> 50 people like, see section 2.7.1 6> 20 People recommended, see section 2.7.2 7> Type: Individual 8> Connect, see section 2.6 point:8 9> Like it, see section 2.7.1 10> Recomend it, see section 2.7.2 11> Bookmark, see section 2.7.3 12> Service description, see section 2.7 13> Area: Popular location 14> F and G icon 15> Profile Picture 16> View profile button, Will redirect to users profile page. * This section will be completed in section 4.2 | * What do you mean by "Type: Individual"? * Few profile list are in grey background. And few are white. What is the meaning for the background colors? | 0
4.2.2 | Save Search | 1> Search tagline 2> Add | * Where does user can edit or delete saved search criteria? | 0.25
4.3 | Report Abuse | 1> User must be login to report abuse. 2> Your Message 3> Add | * Did found any link in front end from where user can report abuse. | 0.25
4.4 | Send Message To Members | * This section will be completed in section 2.4 | * Did found any link in front end from where user can send message. | 0
4.5 | Reference | 1> List the users who referred this user. | * Did found any link in front end from where user can make reference. | 0.25
4.6 | Reviews | 1> User Profile photo 2> User full name 3> star icons with review points | * Did found any link in front end from where user can make reviews. * What is the purpose of this page? | 0.5
4.7 | Sign up | * This section will be completed in section 2.1 |  | 0
4.8 | Login | * This section will be completed in section 2.1 |  | 0
4.9 | Change Country | 1> Will change the entire database from india to usa database. And vise versa. |  | 5
|  |  | Total Man Days | 58
|  |  | Total Business Days | 58
|  |  | Total Calander Months | 2.6364

## No wireframe found
Sr. No | Section | Task Details | Notes | Estimated Time Man Days
2.2.2 | Tweet My Profile |  | * What to do?
2.2.4 | Be a Guru Verified | 1> Verified 2> Facebook connect 3> Unverified 4> Phone number verify. Add a phone number. 5> Make Me feature. What is the process? 6> Add more services. What will happen when a user clicks here? | * The left side menu has changed. * What do you mean by verified and unverified on "http://91.biz/o/guru/guru_listed_21sep/guru/Profile/trust_1.jpg" * After add a phone number Where does the user will put the verification code? | 0
2.2.5 | Verify your mobile | No wire frame found. | What to do? | 0
2.6.1 | Know About Service | No wire frame found. |  | 0
2.6.2 | Add your friend | No wire frame found. |  | 0
2.7.1 | Like it | No wire frame found. |  | 0
2.7.2 | Recomend it | No wire frame found. |  | 0
2.7.3 | Bookmark | No wire frame found.
2.7.4 | Contact Me | No wire frame found.
2.7.5 | View full profile | No wire frame found.
2.7.7 | Write Testimonial | 1> Submit the feedback form. No wire frame found.
2.8 | Inbox | No wire frame found.
2.9 | Notification | As per discussion 4Oct, this is not in this scope of project.
2.10 | Testimony | No wire frame found.
3.2.1 | Service / Category Name |  | * Where should this link goto?
|  |  | Total Man Days | 58
|  |  | Total Business Days | 58
|  |  | Total Calander Months | 2.64